## 2021 WORKBAR HELP DESK PROJECTS
Ticket Number | PROJECT | LOCATION | COMMUNITY MANAGER | DATE REQUESTED | TARGET DATE | PROJECT REQUEST | NEXT STEPS | SUPPORT/ RESOURCE | STATUS | INTERNAL COMMENTS
| CM Training | *All Sites | WB IT Support | 2021-06-29 | 2021-07-30 | Develop and schedule continuing education for CMs |  | Help Desk McLaughlin | In Process
| Cafe Events | *All Sites | WB IT Support | 2021-06-29 | 2021-07-30 | Test "Event" equipment. Speakers, projectors, screens, microphones, HDMI |  | Help Desk Morash | In Process | COVID had left the event equipment dormant for 1 year and should be tested
| Door Access | *All Sites | WB IT Support | 2021-06-28 | 2021-07-30 | Add Mobile Access to S2 Card Readers | Confirm Dates and API info | McLaughlin Tesla | In Process | Bob O'Rourke has ordered new reader for test in Needham. Waiting for API information. Follow Up needed
| Asset Inventory | *All Sites | WB IT Support | 2021-06-29 | 2021-07-30 | Complete inventory of IT and AV equipment assets |  | Help Desk McLaughlin | In Process | Determine asset inventory of WB staff and high value AV investment equpment
| WiFi Test | *All Sites | WB IT Support | 2021-06-29 | 2021-07-30 | Set up "back-door" test SSID for Wobbe Splash Page issues |  | GigXero McLaughlin | DONE | In an effort to trouble shoot member issues, a separate SSID can be used to isolate Wobbe and Connection issues
| AIRTAME PROJECT | *All Sites | WB IT Support | 2021-06-28 | 2021-07-30 | Add Airtame to all client-facing meeting rooms | Order (19) Airtames | McLaughlin | In Process | Complete new order and install of Airtames and Owls per directive
[7 empty] | Order (11) OWLS | Colby
[7 empty] | Order Power Supplies | Mary
[7 empty] | Schedule Teltech | Mary
[7 empty] | Schedule Conference Rooms on WOBBE | Mary
| # 4742 - REPAIR EVENTS BOARD | Cambridge | tamara.clouden@workbar.com | 2021-06-15 | 2021-07-07 | Events board in 1st floor cafe stopped displaying. It is displaying a black countdown screen. | Hardware issue - new hardware will be installed on Thursday, 6/24 Working on pricing from Crestron | Aiello Help Desk Morash | In Process | From Mary: Did hardware ever get installed?

## OPEN HELP DESK TICKETS
TICKET # | LOCATION | COMMUNITY MANAGER | MEMBER CONTACT | DATE REQUESTED | STATUS | ISSUE | REQUEST/TASK | DISPATCH INFO | SUPPORT/ RESOURCES | INTERNAL COMMENTS
4842 | School Street | Alysha McCluskey |  | 2021-07-19 | In Process | Printing | Spots on printer |  | Colby McLaughlin
4836 | Norwell | Sharada Ford | Trimco - Office 204 | 2021-07-16 |  | Printing | Look at network installed and move printer |  | McLaughlin | MM emailed Trimco and will follow up with Norwell team.
4839 | Norwood | Katleen Francois | Wende Malster | 2021-07-15 | In Process Waiting on Reply | WiFi | Wifi dropping user. | Spoke to Kat, opened ticket with Gig Xero,emailed Wendy. Gig Xero rebooted on 7/15 and want Wende to test again. | GigXero McLaughlin | Did Wende test the connection? 7/15, 5pm
Email Ticket | School Street | Alysha McCluskey |  | 2021-07-12 | In Process Waiting on Reply | Printing | Quality of printing at School Street. | MM emailed Mike Marchesi @ Kyocera. Waiting on Mike Marchesi's reply. | Kyocera McLaughlin | Waiting for Mike Marchesi to respond, 7/15.
Email Ticket | School Street | Alysha McCluskey | Jess Jones @ jess@tvisioninsights.com | 2021-07-08 | In Process | Networking | Understand networking options. What's the default connection? | Need: Static AP address, bandwith utilization, discuss access points and conflicts. | McLaughlin | MM to follow up on all items.
4821 | Burlington | Joelisa Tomaszewski |  | 2021-07-07 | In Process Waiting on Info | Phone | 617 number listed on website for “contact” keeps on disconnecting after being put on hold. | Mike and Joelisa reviewed 8x8 phone tree 7/9 @12pm. Waiting on more info from Joelisa re 8x8 phone tree. | McLaughlin
Email Ticket | Norwood | Katleen Francois | Denise Flynne @ denise@nrrchamber.com | 2021-07-06 | Follow Up In Process | Phone | How does billing work for Neponset River phones? What is the estimated cost? | MM to check with Kat. | McLaughlin
4775 | School Street | Alysha McCluskey | Not Applicable | 2021-06-29 | Follow Up In Process | Printing | Need new printer. 4 unsuccessful maintenance attempts, inconsistent printing affecting member experience. | Kyocera sent tech - replaced more parts and not the printer. Tested and need to follow up on quality. Mclusky on vacation until | Kyocera | Need to respond to Alysha.
4774 | Back Bay |  | Kara Hogan at backbay@workbar.com | 2021-06-28 | Follow Up In Process | Furniture | The conference table in Park Meeting Room is wobbly. | MM to find out what the hell this is | McLaughlin | No response to Kara or anyone as of 6/28/21
Email Ticket | Burlington | Joelisa Tomaszewski | Pratyusha Kongara - @Pratyusha Kongara and Janire Valerio- janire.valerio@blinkhealth.com | 2021-06-16 | Follow Up In Process | Networking | Setting up new office and network. | Need to confirm desired physical location for the equipment (suite or data room) | McLaughlin | Need to email Pratyusha and Janire to set up call to discuss requirements and answer questions.
4742 | Cambridge | Tamara Clouden |  | 2021-06-15 | In Process Waiting on Reply | Electronic | Events board in 1st floor cafe stopped displaying. It is displaying a black countdown screen. | Equipment ordered and arriving 7/12. Replacement Raspberry Pi and moved sim memory card to the new one, but replacement unit will not bring screen back with information. MM emailed Steve Codd to get Dev support on this issue. | Codd McLaughlin | MM told Joelisa/Tamara it is a hardware issue and new hardware will be installed on Thursday, 6/24
Email Ticket |  | Lauren Coyle | Floating CM Stanley Michaud-stanley.michaud@workbar.com | 2021-06-14 | Follow Up In Process | Phone | 8x8 phone number for new Floating CM Stanley Michaud? | Get 8x8 # - email Stanley Michaud @ stanley.michaud@workbar.com | McLaughlin | Told Lauren on 6/14 would set up 8x8 # and follow up.
4707 | Cambridge | Tamara Clouden | Tara Nicola | 2021-05-25 | In Process Pending Approval | WiFi | Tara Nicola, Account 7745 is experiencing spotty connection while outdoors. | Pending approval for the cost of $1200.00 | McLaughlin | MM told Tara on 6/23 that outdoor AP has been failing and is currently out of support with manufacturer. Confirming replacement costs.

## LEGACY PROJECTS
Ticket Number | PROJECT | PROJECT REQUEST | DATE REQUESTED | TARGET DATE | PROJECT CONTACT | SUPPORT/ RESOURCE | NEXT STEPS | INTERNAL COMMENTS | STATUS
| CBS/WBZ |  |  |  |  | McLaughlin
| Henry Nevins |  | 2021-06-29 | 2021-07-30 |  |  |  |  | In Process
Henry Nevins
Majestic Construction

## DATA SHEET
STATUS
DONE
In Process
SUPPORT/RESOURCE
Help Desk
McLaughlin
Teltech